## Checklist
Client onboarding checklist
Client:
Start date:
When | Task | Who | Done | Notes
Before kickoff | Send proposal or quote and get written acceptance | You
Before kickoff | Send contract or scope document for signature | You
Before kickoff | Send the deposit invoice | You
Before kickoff | Confirm the deposit has arrived before starting work | You
Before kickoff | Create a project folder and a shared client folder | You
Before kickoff | Send the welcome email with how you work and response times | You
Before kickoff | Send the intake questionnaire | You
Before kickoff | Client completes the intake questionnaire | Client
Before kickoff | Client provides logins, files and brand assets | Client
Before kickoff | Name the client contact who approves work and payment | Client
Kickoff | Hold the kickoff call and record decisions | Both
Kickoff | Confirm scope, deliverables and what is not included | Both
Kickoff | Agree on dates for the first draft and each feedback round | Both
Kickoff | Agree on how feedback is given (one consolidated list) | Both
Kickoff | Send a recap email within 24 hours | You
Week 1 | Share the first progress update | You
Week 1 | Check that the client has everything they owe you | You
Week 1 | Log hours against the estimate | You
Week 1 | Flag any scope change and quote it in writing | You
Week 1 | Check in: anything unclear or worrying? | Both
Progress
Type Y in the Done column. Change, add or delete tasks to fit how you work.